## Sheet1
Risk ID | Date Registered | Risk Area | Risk description | Liklihood of risk occurring (low,medium,high) | Negative impact of risk (low,medium,high) | Project Impact | Proximity/Length of Impact | Response Strategy
1 | 18/12/2020 | Covid19 | Becoming ill and incapable of completing project work due to contraction of coronavirus | high | medium | Likely to be a few days where developer is incapable of completing project work - would set back target completion date for project | On average, symptoms persist for 5 days, but may be longer in special cases | Contact trainer to let them know, try to catch up once recovered, request later due date for project if necessary, but also be prepared for a failure to complete the project if symptons are severe and long lasting
2 | 18/12/2020 | Poor internet connection | Wifi/internet connection available to the developer is insufficient - they have problems accessing a stable and secure connection | medium | medium/high | Most, if not all, project work requires internet connection for completion; project work cannot be sufficiently completed (impact is relative to the severity of the connection problems) | No longer than a few days - it is usually possible to resolve this issue in good time | Get a booster to increase the speed of internet, fix faulty wifi router, get an ethernet cable etc.
3 | 30/12/2020 | Broken Laptop | Laptop is broken/not working properly (this could be due to spilling something on the laptop, dropping it, the laptop being too old, etc.) | low | medium/high | Project work is put on hold; one cannot complete any of the project spec without access to a laptop | A few days, depending on severity of damage and accessibility to service which can provide a new laptop | Get yours fixed (if possible), in the meantime let QA know and request a company laptop if necessary
4 | 30/12/2020 | Family Emergency | Developer experiences some kind of emergency/incident involving their immediate family (i.e. unforseen death of a family member) | low | low/medium/high(varies depending on extent of family emergency | Depends on extent of emergency - developer may need to take time to deal with emergency, during which project cannot be completed. Other emergencies may allow for project completion | Varies depending on family emergency at hand | Contact QA trainer explaining the situation at hand, take time to deal with it and try to catch up once situation is handled - request later project due date if necessary
5 | 30/12/2020 | Lack of Knowledge | Lack of knowledge around subject area at hand in the project - perhaps being unfamiliar with necessary concepts or applications required to complete project work | medium | low | Not too much of an impact on project completion - time and work is required to learn and fill in gaps in the required knowledge, but this should only cause a minor set back | As long as it takes to fill in the gaps in ones knowledge - usually several hours of research/learning will be required (outside of academy training time if necessary) | Fill in the gaps in ones knowledge - conduct research and learning to do so, and speak to trainer if they can help with improving the knowledge that one is lacking
6 | 2021-03-01 | Developing an application that does not function in accordance with the required specification | The developer builds an application/database that functions incorrectly and does not/cannot meet the project requirements | low | medium | Work must be re-completed in the project to correct the errors at hand | At least a few days would likely be necessary to correct mistakes and correct other aspects of the project which have been hindered due to the mistakes made | Address where the developing went wrong and how to correct the mistakes - proceed to do so as quickly as possible, ensuring to note the effects of the mistakes in other aspects on the projects
7 | 2021-03-01 | Technical problems | Errors/problems/bugs in the software that the developer relies on using for the completion of the project (e.g. java/sql have bugs that need fixing) | low | medium | A bug or fault in the software would disrupt the development process and cause problems in the continuous integration pipeline, consequently the project would be put on halt while these disruptions take place | No longer than a few days - it is possible to change to a different version of the software or use a different application all together to continue with the completion of the project (so long as work has been saved along the way) | Make sure to use releases/versions of software that is stable and reliable, and where necessary the developer should move to and use alternative software.
8 | 2021-03-01 | Time management issues | Developer requires more time than they estimated they would to complete project tasks - they have incorrectly managed their time scales | medium | medium | Could result in project being incomplete when it is due to be compelted, or, to avoid this, there will be extra time spent on project (outside of sociable hours) | Depends on size of issues if it's just that 1 PBI takes longer than expected, it can be passed to next sprint and length of impact would not be large, but if large part of project is behind, proximity of impact is greater | Schedule in the additional time required to complete tasks and complete the time-sensitive project. Speak to trainer if the severity of the issue is great and it seems likely that the project will not be completed in time
9 | 2021-03-01 | Additional requirements | There are additional things required for the completion of the project that the developer does not account for | low | medium/high | Could be detrimental if the requirements are not realised in time | Time it takes to complete the requirements - could be large or small but likely to have noticable effect on project completion time | Complete additional requirements that project is missing, attempting to do so in time for hand in date